## Guidance
STEP-BY-STEP GUIDE I. Developing your workplan 1. Step 1: Define Your Project Goals Start by clearly identifying the overall goals of your project. What do you want to achieve by the end of the program? Ensure that your goals are specific, measurable, and aligned with your startup’s objectives. Example: If your goal is to increase user engagement, your project goal could be "Acquire 200 new users by the end of the program." Step 2: Break Down Goals into Expected Outputs Translate your goals into concrete deliverables or Expected Outputs. These are the specific results you plan to achieve. You will break your goals into smaller, actionable outputs that are easier to track and manage. Example Output: Output 1.1: Develop and launch a marketing campaign to acquire 200 new users. Step 3: Set Indicators to Measure Success For each expected output, define Indicators—measurable metrics that will track whether you’re making progress toward your output. Each output may have multiple indicators to fully measure success. Steps: Identify the Baseline (the current status). Set a Target (what you aim to achieve). Step 4: Set a Time Frame Determine the timeline for achieving each output and indicator. Be realistic about how long each task will take, and establish clear deadlines. Step 5: Identify Means of Verification For each indicator, specify how you will verify that it has been achieved. These are the data sources or evidence you will use to show that the expected output has been met. Step 6: Estimate the Budget Break down the detailed budget in the budget sheet. Step 7: Review and Adjust II. Complete your budget plan 1. Enter Basic Information: Fill in the Date. Enter the Name of the Recipient (Startup team). 2. List Each Activity: Identify each Activity 1, Activity 2, etc. Break down activities into specific tasks or services. 3. Final Check: Review each activity and ensure all costs are categorized and calculated correctly. Add necessary notes to clarify any significant amounts or unusual items. III. Prepare for Progress and Financial Reporting Once your project is underway, it’s crucial to regularly report on both progress and financial use. This ensures transparency, allows you to track performance, and helps to identify any adjustments needed. | Term | Description
| Expected Outputs | These are the tangible results or deliverables your team aims to achieve. They should be specific and aligned with the objectives of your project. For example, if your project is about increasing user engagement, an output could be "200 new users signed up."
| Indicators | These are measurable metrics used to assess whether the expected outputs have been achieved. For each output, you will set up one or more indicators. For instance, if your output is "200 new users," the indicator could be "number of new users signed up."
| Time Frame | The period in which you plan to achieve each output. This is essential for tracking progress and ensuring timely completion. It can be broken down into days, weeks, or months depending on the scale of your project.
| Means of Verification | This refers to the sources of evidence or data that will be used to prove that the outputs have been achieved. Examples include customer surveys, platform analytics, or sales reports.
| Estimated Budget | This is the projected cost required to achieve each output. It includes any resources (e.g., personnel, tools, software, materials) needed to complete the work. The budget should be realistic and justifiable based on your expected outcomes.
When making purchases, startups are required to provide supporting documents. Please refer to this link to ensure compliance with Vietnam’s financial and accounting regulations. Link: https://sme.misa.vn/63137/tong-hop-10-bo-chung-tu-quan-trong-cua-mot-so-khoan-chi-phi-tai-chinh-ke-toan-can-nam-ro/

## Budget
THE GLOBAL ENTREPREP INCUBATOR 2025
Budget / Schedule of Estimated Expenditures
Date:
Name of the Recipient (Startup teams)
Duration:
Eligible Seed Grant Amount:
| Description | Output | Unit (e.g. person, vehicle, room, unit, …) | Quantity | Eligible up to in USD | Total in USD | Total in VND (in thousand) | Notes (reference to the amount)
Total: Direct costs
When adding new lines, please make sure your formulas is correct.
Please note: The grant funds must be strictly allocated towards indicators that directly support the startup's objectives and the achievement of key business milestones as outlined in the startup’s project plan. Expenses unrelated to the core development and execution of the business, such as staffing costs, per-diems, allowances, and general administrative overhead (including office rent, telephone bills, internet, stationery, etc.), are not permitted. The grant should focus on driving tangible progress in product development, market validation, customer acquisition, and other essential startup activities. Any use of the grant beyond these specified purposes requires prior written approval.

## Work Plan
THE WORK PLAN OF THE STARTUP
Date:
Name of the Recipient (Startup teams):
Eligible Seed Grant Amount:
Project name:
Details of the proposed project (eg problems/solutions/target users (max 150 words)
Names of other team members:
Expected Outputs | Indicators | Time frame | Means of Verification | Estimated budget
1. Additional outputs can be added or deleted as apporpriate
2. Additional rows can be added where there are more output indicator
3. Additional rows for your big goal can be added if there's a bigger result contributed by the outputs
THE STARTUP | Your signature here

## Report
THE REPORT OF THE STARTUP __________________
Date:
Name of the Recipient (Startup teams):
The purpose of this section is to understand how the project actually performed against what it intended to accomplish. This should be done through the verification of the indicators of achievement that were developed in the project document as well as through an assessment of the implemented activities.
Entities are kindly requested to fill in the tables below. Startup teams are asked to fill and verified in the table below with accurate figures for each indicator.
Startups are requested to submit this report through email to elab@vinuni.edu.vn following this timeline: Submission Timelines: First progress report: within 2 weeks after the disbursement of the grant. Final report: 1/10/2025. Failure to submit either the progress or final report will result in the startup being considered non-compliant, leading to the reimbursement of disbursed funds to VinUni, as per the grant agreement terms.
Table 1 - Review of Performance Indicators
Expected Outputs | Indicators | Description | Expected Indicator of achievement (T0) | Actual Indicator of achievement (T1) | Variance Analysis
THE STARTUP Signed by for and on behalf of TEAM